## Logical framework
LOGICAL FRAMEWORK 3MPS
| Intervention logic | Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall Objective | This overall objective of the pillar is to address the issue of environmental quality, with respect to marine, coastal and terrestrial ecosystems in the Region. Environmental quality is essential for underpinning human activities in the Region and for ensuring economic and social well-being for its peoples. The pillar will deal with the environmental issues that can only be adequately tackled through cooperation at the level and scale of the macro-region. | At least 3 actions, project activities in line with the specific objectives. Additional one TSG3 meeting per year and workshops | Annual Reports of TSG 3 and GB EUSAIR
Specific Objective | 1. To ensure a good environmental and ecological status of the marine and coastal environment by 2020 in line with the relevant EU acquis and the ecosystem approach of the Barcelona Convention. 2. To contribute to the goal of the EU Biodiversity Strategy to halt the loss of biodiversity and the degradation of ecosystem services in the EU by 2020, and restore them in so far as feasible, by addressing threats to marine and terrestrial biodiversity. 3. To improve waste management by reducing waste flows to the sea and, to reduce nutrient flows and other pollutants to the rivers and the sea. | • Establishment of a common infrastructure platform with participation of all countries for data collection, research, and laboratory analysis by end of 2015 • 10% surface coverage of Adriatic and Ionian Seas by Marine Protected areas26 • Enhancement of NATURA 2000 and Emerald networks in the Region • Achieving Good Ecological Status of the Adriatic and Ionian Seas by 2020 • Enhancement of a marine NATURA 2000 network and a coherent and representative network of MPAs under the Marine Strategy Framework Directive by 2020 • Reduction of anthropogenic nutrient flows to the Adriatic and Ionian seas to ensure that by 2021 eutrophication is minimised Reduction of marine litter in line with Marine Strategy Framework Directive and 7th Environment Action Programme targets by 2020 • A joint contingency plan for oil spills and other large scale pollution events adopted by 2016 and measures to enable joint and coordinated emergency response implemented by 2020 • Establishment of transnational management plans for all terrestrial eco-regions, shared by two or more participating countries • Adoption of maritime spatial planning and integrated coastal management strategies by EU Member State by 2017 and for coastal candidate and potential candidate Countries by 2018 | Implementarion report of EUSAIR Action Plan in 2020+ and Annual reports of TSG3 | No quorum at the meeting. The EUSAIR Implementation plan will not be implemented
Expected results | Addressing the threats to biodiversity caused by human activities, like deterioration of water quality (in particular impact of marine litter, micro plastic and chemical pollutants) and because of climate change. | What are the indicators to measure whether and to what extent the action achieves the expected results? - Common solution to be foreseen in the project implementation phase about: legal bases, governance and technical aspects. - Identification of stakeholders - Pilot project - Pilot monitoring activities | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
Activities | What are the key activities to be carried out and in what sequence in order to produce the expected results? (group the activities by result) WP:preparation activities - TSG 3 EUSAIR preparation conferences and meetings Other WP: - Drafting a proposal for concrete measures for monitoring and management of marine protected species. - Developing an Adriatic-Ionian Observatory to improve data collecting and sharing. - Identification of hot spot marine biogenic formations that are excluded from Marine protected areas or are not adequately managed within those with pilot monitoring to assess their environmental status and preparation of common sampling protocols. - Evaluating the status of the selected marine protected species due to risks related to pollutants (e.g. marine litter, microplastics) and climate change with the support of pilot projects. - Preparing a plan for raising awareness education of stakeholders, local communities and tourist on the effects of tourism, human activities as such and of marine litter on marine protected species and popularisation through citizen science. -The excellent back ground for the project are the results and outputs of the Trecorala, ClimaParks, ActionMed, MEDCIS, NetCet, Tartalife, DeFishGear and other relevant projects (studies, analysis and protocols). | Means: What are the means required to implment these activities; personel, equipment, trining, studies, supplies, operational facilities etc. PARTNERS LEAD PARTNER: National Institute of Biology (NIB), Marine Biology Station, Potential project partners: GREECE: Zakynthos National Park ITALY: IMELS - PNM; Friuli Venezia Giulia Region Other Italian Regions and/or Regional Agencies for Environmental Protection (ARPA) (TBC) MONTENEGRO: Environment and Nature Protection Agency Institute for Marine Biology SLOVENIA: National Institute of Biology (NIB), Marine Biology Station, Večna pot 111, 1000 Ljubljana Institute for Water of the Republic of Slovenia, Dunajska cesta 156, 1000 Ljubljana POTENTIAL BIH PARTNERS: Centar za životnu sredinu or REC Bosnia and Herzegovina CROATIA: Croatian Agency for the Evnironment and Nature (CAEN), Address: Radnička cesta 80/7, 10 000 Zagreb National Park Brijuni, Address: Brionska 10, 52212 Fažana JU NP Kornati - Public institution Kornati, Address: Butina 2, Murter 22243 National Park Mljet, Address: Pristanište 2, 20226 Goveđari - Mljet National Park Krka, Address: Trg Ivana Pavla II br.5, 22000 Šibenik JU PP Lastovo - Public institution “Lastovo Islands Nature Park”, Address: Trg Sv. Petra 7, 20289 Ubli JU PP Telašćica - Public institution "Nature Park Telašćica„, Address: Sali X 1, 23281 Sali Veterinarski fakultet - Faculty of Veterinary Medicine, Address: Heinzelova 55, 10 000 Zagreb IOR-Split - Institute of Oceanography and Fisheries, Address: Šetalište I. Meštrovića 63, 21000 Split Institut Plavi svijet-Mali Lošinj - Blue World Institute of Marine Research and Conservation, Address: Kaštel 24, HR-51551 Veli Lošinj IRB CIM-Rovinj, Address: Bijenička cesta 54, 10000 Zagreb Aquarium Pula-Centar za oporavak morskih životinja, Address: Verudela b.b., 52105 Pula NGO Sunce, Address: Obala hrvatskog narodnog preporoda 7, 21000 Split PMF, Biološki odsjek - FACULTY OF SCIENCE, UNIVERSITY OF ZAGREB Biology department, Address: Rooseveltov trg 6., 10000 Zagreb WWF Adria, Address: Zelinska 2, 10 000 Zagreb | What are the sources of infomration about action progress. COSTS What are the action costs? Hoe are they classified? (Budget for Action Brakdown) | What pre-conditions are required before the action starts? What condistions outside the Beneficary's direct control have to be met for the implementation of planned activities?

## LF Albania
LOGICAL FRAMEWORK 3MPS
| Intervention logic | Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall Objective | This overall objective of the pillar is to address the issue of environmental quality, with respect to marine, coastal and terrestrial ecosystems in the Region. Environmental quality is essential for underpinning human activities in the Region and for ensuring economic and social well-being for its peoples. The pillar will deal with the environmental issues that can only be adequately tackled through cooperation at the level and scale of the macro-region. | At least 3 actions, project activities in line with the specific objectives. Additional one TSG3 meeting per year and workshops | Annual Reports of TSG 3 and GB EUSAIR
Specific Objective | 1. To ensure a good environmental and ecological status of the marine and coastal environment by 2020 in line with the relevant EU acquis and the ecosystem approach of the Barcelona Convention. 2. To contribute to the goal of the EU Biodiversity Strategy to halt the loss of biodiversity and the degradation of ecosystem services in the EU by 2020, and restore them in so far as feasible, by addressing threats to marine and terrestrial biodiversity. 3. To improve waste management by reducing waste flows to the sea and, to reduce nutrient flows and other pollutants to the rivers and the sea. | • Establishment of a common infrastructure platform with participation of all countries for data collection, research, and laboratory analysis by end of 2015 • 10% surface coverage of Adriatic and Ionian Seas by Marine Protected areas26 • Enhancement of NATURA 2000 and Emerald networks in the Region • Achieving Good Ecological Status of the Adriatic and Ionian Seas by 2020 • Enhancement of a marine NATURA 2000 network and a coherent and representative network of MPAs under the Marine Strategy Framework Directive by 2020 • Reduction of anthropogenic nutrient flows to the Adriatic and Ionian seas to ensure that by 2021 eutrophication is minimised Reduction of marine litter in line with Marine Strategy Framework Directive and 7th Environment Action Programme targets by 2020 • A joint contingency plan for oil spills and other large scale pollution events adopted by 2016 and measures to enable joint and coordinated emergency response implemented by 2020 • Establishment of transnational management plans for all terrestrial eco-regions, shared by two or more participating countries • Adoption of maritime spatial planning and integrated coastal management strategies by EU Member State by 2017 and for coastal candidate and potential candidate Countries by 2018 | Implementarion report of EUSAIR Action Plan in 2020+ and Annual reports of TSG3 | No quorum at the meeting. The EUSAIR Implementation plan will not be implemented
Expected results | Addressing the threats to biodiversity caused by human activities, like deterioration of water quality (in particular impact of marine litter, micro plastic and chemical pollutants) and because of climate change. | What are the indicators to measure whether and to what extent the action achieves the expected results? - Common solution to be foreseen in the project implementation phase about: legal bases, governance and technical aspects. - Identification of stakeholders - Pilot project - Pilot monitoring activities | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
Activities | What are the key activities to be carried out and in what sequence in order to produce the expected results? (group the activities by result) WP:preparation activities - TSG 3 EUSAIR preparation conferences and meetings Other WP: - Drafting a proposal for concrete measures for monitoring and management of marine protected species. - Developing an Adriatic-Ionian Observatory to improve data collecting and sharing. - Identification of hot spot marine biogenic formations that are excluded from Marine protected areas or are not adequately managed within those with pilot monitoring to assess their environmental status and preparation of common sampling protocols. - Evaluating the status of the selected marine protected species due to risks related to pollutants (e.g. marine litter, microplastics) and climate change with the support of pilot projects. - Preparing a plan for raising awareness education of stakeholders, local communities and tourist on the effects of tourism, human activities as such and of marine litter on marine protected species and popularisation through citizen science. -The excellent back ground for the project are the results and outputs of the Trecorala, ClimaParks, ActionMed, MEDCIS, NetCet, Tartalife, DeFishGear and other relevant projects (studies, analysis and protocols). | Means: What are the means required to implment these activities; personel, equipment, trining, studies, supplies, operational facilities etc. PARTNERS Potential project partners: | What are the sources of infomration about action progress. COSTS What are the action costs? Hoe are they classified? (Budget for Action Brakdown) | What pre-conditions are required before the action starts? What condistions outside the Beneficary's direct control have to be met for the implementation of planned activities?

## LF Bosnia and Herzegovina
LOGICAL FRAMEWORK 3MPS
| Intervention logic | Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall Objective | This overall objective of the pillar is to address the issue of environmental quality, with respect to marine, coastal and terrestrial ecosystems in the Region. Environmental quality is essential for underpinning human activities in the Region and for ensuring economic and social well-being for its peoples. The pillar will deal with the environmental issues that can only be adequately tackled through cooperation at the level and scale of the macro-region. | At least 3 actions, project activities in line with the specific objectives. Additional one TSG3 meeting per year and workshops | Annual Reports of TSG 3 and GB EUSAIR
Specific Objective | 1. To ensure a good environmental and ecological status of the marine and coastal environment by 2020 in line with the relevant EU acquis and the ecosystem approach of the Barcelona Convention. 2. To contribute to the goal of the EU Biodiversity Strategy to halt the loss of biodiversity and the degradation of ecosystem services in the EU by 2020, and restore them in so far as feasible, by addressing threats to marine and terrestrial biodiversity. 3. To improve waste management by reducing waste flows to the sea and, to reduce nutrient flows and other pollutants to the rivers and the sea. | • Establishment of a common infrastructure platform with participation of all countries for data collection, research, and laboratory analysis by end of 2015 • 10% surface coverage of Adriatic and Ionian Seas by Marine Protected areas26 • Enhancement of NATURA 2000 and Emerald networks in the Region • Achieving Good Ecological Status of the Adriatic and Ionian Seas by 2020 • Enhancement of a marine NATURA 2000 network and a coherent and representative network of MPAs under the Marine Strategy Framework Directive by 2020 • Reduction of anthropogenic nutrient flows to the Adriatic and Ionian seas to ensure that by 2021 eutrophication is minimised Reduction of marine litter in line with Marine Strategy Framework Directive and 7th Environment Action Programme targets by 2020 • A joint contingency plan for oil spills and other large scale pollution events adopted by 2016 and measures to enable joint and coordinated emergency response implemented by 2020 • Establishment of transnational management plans for all terrestrial eco-regions, shared by two or more participating countries • Adoption of maritime spatial planning and integrated coastal management strategies by EU Member State by 2017 and for coastal candidate and potential candidate Countries by 2018 | Implementarion report of EUSAIR Action Plan in 2020+ and Annual reports of TSG3 | No quorum at the meeting. The EUSAIR Implementation plan will not be implemented
Expected results | Addressing the threats to biodiversity caused by human activities, like deterioration of water quality (in particular impact of marine litter, micro plastic and chemical pollutants) and because of climate change. | What are the indicators to measure whether and to what extent the action achieves the expected results? - Common solution to be foreseen in the project implementation phase about: legal bases, governance and technical aspects. - Identification of stakeholders - Pilot project - Pilot monitoring activities | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
Activities | What are the key activities to be carried out and in what sequence in order to produce the expected results? (group the activities by result) WP:preparation activities - TSG 3 EUSAIR preparation conferences and meetings Other WP: - Drafting a proposal for concrete measures for monitoring and management of marine protected species. - Developing an Adriatic-Ionian Observatory to improve data collecting and sharing. - Identification of hot spot marine biogenic formations that are excluded from Marine protected areas or are not adequately managed within those with pilot monitoring to assess their environmental status and preparation of common sampling protocols. - Evaluating the status of the selected marine protected species due to risks related to pollutants (e.g. marine litter, microplastics) and climate change with the support of pilot projects. - Preparing a plan for raising awareness education of stakeholders, local communities and tourist on the effects of tourism, human activities as such and of marine litter on marine protected species and popularisation through citizen science. -The excellent back ground for the project are the results and outputs of the Trecorala, ClimaParks, ActionMed, MEDCIS, NetCet, Tartalife, DeFishGear and other relevant projects (studies, analysis and protocols). | Means: What are the means required to implment these activities; personel, equipment, trining, studies, supplies, operational facilities etc. PARTNERS Potential project partners: | What are the sources of infomration about action progress. COSTS What are the action costs? Hoe are they classified? (Budget for Action Brakdown) | What pre-conditions are required before the action starts? What condistions outside the Beneficary's direct control have to be met for the implementation of planned activities?

## LF Croatia
LOGICAL FRAMEWORK 3MPS
| Intervention logic | Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall Objective | This overall objective of the pillar is to address the issue of environmental quality, with respect to marine, coastal and terrestrial ecosystems in the Region. Environmental quality is essential for underpinning human activities in the Region and for ensuring economic and social well-being for its peoples. The pillar will deal with the environmental issues that can only be adequately tackled through cooperation at the level and scale of the macro-region. | At least 3 actions, project activities in line with the specific objectives. Additional one TSG3 meeting per year and workshops | Annual Reports of TSG 3 and GB EUSAIR
Specific Objective | 1. To ensure a good environmental and ecological status of the marine and coastal environment by 2020 in line with the relevant EU acquis and the ecosystem approach of the Barcelona Convention. 2. To contribute to the goal of the EU Biodiversity Strategy to halt the loss of biodiversity and the degradation of ecosystem services in the EU by 2020, and restore them in so far as feasible, by addressing threats to marine and terrestrial biodiversity. 3. To improve waste management by reducing waste flows to the sea and, to reduce nutrient flows and other pollutants to the rivers and the sea. | • Establishment of a common infrastructure platform with participation of all countries for data collection, research, and laboratory analysis by end of 2015 • 10% surface coverage of Adriatic and Ionian Seas by Marine Protected areas26 • Enhancement of NATURA 2000 and Emerald networks in the Region • Achieving Good Ecological Status of the Adriatic and Ionian Seas by 2020 • Enhancement of a marine NATURA 2000 network and a coherent and representative network of MPAs under the Marine Strategy Framework Directive by 2020 • Reduction of anthropogenic nutrient flows to the Adriatic and Ionian seas to ensure that by 2021 eutrophication is minimised Reduction of marine litter in line with Marine Strategy Framework Directive and 7th Environment Action Programme targets by 2020 • A joint contingency plan for oil spills and other large scale pollution events adopted by 2016 and measures to enable joint and coordinated emergency response implemented by 2020 • Establishment of transnational management plans for all terrestrial eco-regions, shared by two or more participating countries • Adoption of maritime spatial planning and integrated coastal management strategies by EU Member State by 2017 and for coastal candidate and potential candidate Countries by 2018 | Implementarion report of EUSAIR Action Plan in 2020+ and Annual reports of TSG3 | No quorum at the meeting. The EUSAIR Implementation plan will not be implemented
Expected results | Addressing the threats to biodiversity caused by human activities, like deterioration of water quality (in particular impact of marine litter, micro plastic and chemical pollutants) and because of climate change. | What are the indicators to measure whether and to what extent the action achieves the expected results? - Common solution to be foreseen in the project implementation phase about: legal bases, governance and technical aspects. - Identification of stakeholders - Pilot project - Pilot monitoring activities | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
Activities | What are the key activities to be carried out and in what sequence in order to produce the expected results? (group the activities by result) WP:preparation activities - TSG 3 EUSAIR preparation conferences and meetings Other WP: - Drafting a proposal for concrete measures for monitoring and management of marine protected species. - Developing an Adriatic-Ionian Observatory to improve data collecting and sharing. - Identification of hot spot marine biogenic formations that are excluded from Marine protected areas or are not adequately managed within those with pilot monitoring to assess their environmental status and preparation of common sampling protocols. - Evaluating the status of the selected marine protected species due to risks related to pollutants (e.g. marine litter, microplastics) and climate change with the support of pilot projects. - Preparing a plan for raising awareness education of stakeholders, local communities and tourist on the effects of tourism, human activities as such and of marine litter on marine protected species and popularisation through citizen science. -The excellent back ground for the project are the results and outputs of the Trecorala, ClimaParks, ActionMed, MEDCIS, NetCet, Tartalife, DeFishGear and other relevant projects (studies, analysis and protocols). | Means: What are the means required to implment these activities; personel, equipment, trining, studies, supplies, operational facilities etc. PARTNERS Potential project partners: CROATIA: IOR-Split - Institute of Oceanography and Fisheries Address: Šetalište I. Meštrovića 63, 21000 Split Phone: +385 (0) 21 408000 Web: http://www.izor.hr/web/guest/home Contact person: Nedo Vrgoc vrgoc@izor.hr , Tutman tutman@izor.hr Institut Plavi svijet-Mali Lošinj - Blue World Institute of Marine Research and Conservation Address: Kaštel 24, HR-51551 Veli Lošinj Phone: +385 (0) 51 604 666 Web: https://www.blue-world.org/about-us/about-us-2/ Contact person: Pete Mackelworth peter.mackelworth@gmail.com IRB CIM-Rovinj Address: Bijenička cesta 54, 10000 Zagreb Phone: +385 (0) 1 4561-111 Web: https://www.irb.hr/Istrazivanja/Zavodi/Centar-za-istrazivanje-mora Contact person: dr. sc. Robert Precali predstojnik.cim@irb.hr ; travizi@cim.irb.hr ; jaklin@cim.irb.hr ), Aquarium Pula-Centar za oporavak morskih životinja Address: Verudela b.b., 52105 Pula Phone: +385 (0) 52 381 402 Web: https://www.aquarium.hr/ Contact person:Milena Micic micicmilena1@gmail.com, Karin Gobić Medica karin.gobic@gmail.com NGO Sunce Address: Obala hrvatskog narodnog preporoda 7, 21000 Split Phone: +385 (0) 21 360779 Web: http://sunce-st.org/ Contact person: Zrinka Jakl; zrinka.jakl@sunce-st.org PMF, Biološki odsjek - FACULTY OF SCIENCE, UNIVERSITY OF ZAGREB Biology department Address: Rooseveltov trg 6., 10000 Zagreb Phone: +385 (0) 1 4877 700 Web: http://www.pmf.unizg.hr Contact person: Petar Kružić; petar.kruzic@biol.pmf.hr | What are the sources of infomration about action progress. COSTS What are the action costs? Hoe are they classified? (Budget for Action Brakdown) | What pre-conditions are required before the action starts? What condistions outside the Beneficary's direct control have to be met for the implementation of planned activities?

## LF Greece
LOGICAL FRAMEWORK 3MPS
| Intervention logic | Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall Objective | This overall objective of the pillar is to address the issue of environmental quality, with respect to marine, coastal and terrestrial ecosystems in the Region. Environmental quality is essential for underpinning human activities in the Region and for ensuring economic and social well-being for its peoples. The pillar will deal with the environmental issues that can only be adequately tackled through cooperation at the level and scale of the macro-region. | At least 3 actions, project activities in line with the specific objectives. Additional one TSG3 meeting per year and workshops | Annual Reports of TSG 3 and GB EUSAIR
Specific Objective | 1. To ensure a good environmental and ecological status of the marine and coastal environment by 2020 in line with the relevant EU acquis and the ecosystem approach of the Barcelona Convention. 2. To contribute to the goal of the EU Biodiversity Strategy to halt the loss of biodiversity and the degradation of ecosystem services in the EU by 2020, and restore them in so far as feasible, by addressing threats to marine and terrestrial biodiversity. 3. To improve waste management by reducing waste flows to the sea and, to reduce nutrient flows and other pollutants to the rivers and the sea. | • Establishment of a common infrastructure platform with participation of all countries for data collection, research, and laboratory analysis by end of 2015 • 10% surface coverage of Adriatic and Ionian Seas by Marine Protected areas26 • Enhancement of NATURA 2000 and Emerald networks in the Region • Achieving Good Ecological Status of the Adriatic and Ionian Seas by 2020 • Enhancement of a marine NATURA 2000 network and a coherent and representative network of MPAs under the Marine Strategy Framework Directive by 2020 • Reduction of anthropogenic nutrient flows to the Adriatic and Ionian seas to ensure that by 2021 eutrophication is minimised Reduction of marine litter in line with Marine Strategy Framework Directive and 7th Environment Action Programme targets by 2020 • A joint contingency plan for oil spills and other large scale pollution events adopted by 2016 and measures to enable joint and coordinated emergency response implemented by 2020 • Establishment of transnational management plans for all terrestrial eco-regions, shared by two or more participating countries • Adoption of maritime spatial planning and integrated coastal management strategies by EU Member State by 2017 and for coastal candidate and potential candidate Countries by 2018 | Implementarion report of EUSAIR Action Plan in 2020+ and Annual reports of TSG3 | No quorum at the meeting. The EUSAIR Implementation plan will not be implemented
Expected results | Addressing the threats to biodiversity caused by human activities, like deterioration of water quality (in particular impact of marine litter, micro plastic and chemical pollutants) and because of climate change. | What are the indicators to measure whether and to what extent the action achieves the expected results? - Common solution to be foreseen in the project implementation phase about: legal bases, governance and technical aspects. - Identification of stakeholders - Pilot project - Pilot monitoring activities | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
Activities | What are the key activities to be carried out and in what sequence in order to produce the expected results? (group the activities by result) WP:preparation activities - TSG 3 EUSAIR preparation conferences and meetings Other WP: - Drafting a proposal for concrete measures for monitoring and management of marine protected species. - Developing an Adriatic-Ionian Observatory to improve data collecting and sharing. - Identification of hot spot marine biogenic formations that are excluded from Marine protected areas or are not adequately managed within those with pilot monitoring to assess their environmental status and preparation of common sampling protocols. - Evaluating the status of the selected marine protected species due to risks related to pollutants (e.g. marine litter, microplastics) and climate change with the support of pilot projects. - Preparing a plan for raising awareness education of stakeholders, local communities and tourist on the effects of tourism, human activities as such and of marine litter on marine protected species and popularisation through citizen science. -The excellent back ground for the project are the results and outputs of the Trecorala, ClimaParks, ActionMed, MEDCIS, NetCet, Tartalife, DeFishGear and other relevant projects (studies, analysis and protocols). | Means: What are the means required to implment these activities; personel, equipment, trining, studies, supplies, operational facilities etc. PARTNERS Potential project partners: GREECE: Zakynthos National Park email: info@nmp-zak.org | What are the sources of infomration about action progress. COSTS What are the action costs? Hoe are they classified? (Budget for Action Brakdown) | What pre-conditions are required before the action starts? What condistions outside the Beneficary's direct control have to be met for the implementation of planned activities?

## LF Italy
LOGICAL FRAMEWORK 3MPS
| Intervention logic | Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall Objective | This overall objective of the pillar is to address the issue of environmental quality, with respect to marine, coastal and terrestrial ecosystems in the Region. Environmental quality is essential for underpinning human activities in the Region and for ensuring economic and social well-being for its peoples. The pillar will deal with the environmental issues that can only be adequately tackled through cooperation at the level and scale of the macro-region. | At least 3 actions, project activities in line with the specific objectives. Additional one TSG3 meeting per year and workshops | Annual Reports of TSG 3 and GB EUSAIR
Specific Objective | 1. To ensure a good environmental and ecological status of the marine and coastal environment by 2020 in line with the relevant EU acquis and the ecosystem approach of the Barcelona Convention. 2. To contribute to the goal of the EU Biodiversity Strategy to halt the loss of biodiversity and the degradation of ecosystem services in the EU by 2020, and restore them in so far as feasible, by addressing threats to marine and terrestrial biodiversity. 3. To improve waste management by reducing waste flows to the sea and, to reduce nutrient flows and other pollutants to the rivers and the sea. | • Establishment of a common infrastructure platform with participation of all countries for data collection, research, and laboratory analysis by end of 2015 • 10% surface coverage of Adriatic and Ionian Seas by Marine Protected areas26 • Enhancement of NATURA 2000 and Emerald networks in the Region • Achieving Good Ecological Status of the Adriatic and Ionian Seas by 2020 • Enhancement of a marine NATURA 2000 network and a coherent and representative network of MPAs under the Marine Strategy Framework Directive by 2020 • Reduction of anthropogenic nutrient flows to the Adriatic and Ionian seas to ensure that by 2021 eutrophication is minimised Reduction of marine litter in line with Marine Strategy Framework Directive and 7th Environment Action Programme targets by 2020 • A joint contingency plan for oil spills and other large scale pollution events adopted by 2016 and measures to enable joint and coordinated emergency response implemented by 2020 • Establishment of transnational management plans for all terrestrial eco-regions, shared by two or more participating countries • Adoption of maritime spatial planning and integrated coastal management strategies by EU Member State by 2017 and for coastal candidate and potential candidate Countries by 2018 | Implementarion report of EUSAIR Action Plan in 2020+ and Annual reports of TSG3 | No quorum at the meeting. The EUSAIR Implementation plan will not be implemented
Expected results | Addressing the threats to biodiversity caused by human activities, like deterioration of water quality (in particular impact of marine litter, micro plastic and chemical pollutants) and because of climate change. | What are the indicators to measure whether and to what extent the action achieves the expected results? - Common solution to be foreseen in the project implementation phase about: legal bases, governance and technical aspects. - Identification of stakeholders - Pilot project - Pilot monitoring activities | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
Activities | What are the key activities to be carried out and in what sequence in order to produce the expected results? (group the activities by result) WP:preparation activities - TSG 3 EUSAIR preparation conferences and meetings Other WP: - Drafting a proposal for concrete measures for monitoring and management of marine protected species. - Developing an Adriatic-Ionian Observatory to improve data collecting and sharing. - Identification of hot spot marine biogenic formations that are excluded from Marine protected areas or are not adequately managed within those with pilot monitoring to assess their environmental status and preparation of common sampling protocols. - Evaluating the status of the selected marine protected species due to risks related to pollutants (e.g. marine litter, microplastics) and climate change with the support of pilot projects. - Preparing a plan for raising awareness education of stakeholders, local communities and tourist on the effects of tourism, human activities as such and of marine litter on marine protected species and popularisation through citizen science. -The excellent back ground for the project are the results and outputs of the Trecorala, ClimaParks, ActionMed, MEDCIS, NetCet, Tartalife, DeFishGear and other relevant projects (studies, analysis and protocols). | Means: What are the means required to implment these activities; personel, equipment, trining, studies, supplies, operational facilities etc. PARTNERS Potential project partners: ITALY: IMELS - PNM; Friuli Venezia Giulia Region (Bonetti Marzia marzia.bonetti@regione.fvg.it; Mrs. Reja Elisabetta elisabetta.reja@regione.fvg.it ); Other Italian Regions and/or Regional Agencies for Environmental Protection (ARPA) (TBC) | What are the sources of infomration about action progress. COSTS What are the action costs? Hoe are they classified? (Budget for Action Brakdown) | What pre-conditions are required before the action starts? What condistions outside the Beneficary's direct control have to be met for the implementation of planned activities?

## LF Montenegro
LOGICAL FRAMEWORK 3MPS
| Intervention logic | Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall Objective | This overall objective of the pillar is to address the issue of environmental quality, with respect to marine, coastal and terrestrial ecosystems in the Region. Environmental quality is essential for underpinning human activities in the Region and for ensuring economic and social well-being for its peoples. The pillar will deal with the environmental issues that can only be adequately tackled through cooperation at the level and scale of the macro-region. | At least 3 actions, project activities in line with the specific objectives. Additional one TSG3 meeting per year and workshops | Annual Reports of TSG 3 and GB EUSAIR
Specific Objective | 1. To ensure a good environmental and ecological status of the marine and coastal environment by 2020 in line with the relevant EU acquis and the ecosystem approach of the Barcelona Convention. 2. To contribute to the goal of the EU Biodiversity Strategy to halt the loss of biodiversity and the degradation of ecosystem services in the EU by 2020, and restore them in so far as feasible, by addressing threats to marine and terrestrial biodiversity. 3. To improve waste management by reducing waste flows to the sea and, to reduce nutrient flows and other pollutants to the rivers and the sea. | • Establishment of a common infrastructure platform with participation of all countries for data collection, research, and laboratory analysis by end of 2015 • 10% surface coverage of Adriatic and Ionian Seas by Marine Protected areas26 • Enhancement of NATURA 2000 and Emerald networks in the Region • Achieving Good Ecological Status of the Adriatic and Ionian Seas by 2020 • Enhancement of a marine NATURA 2000 network and a coherent and representative network of MPAs under the Marine Strategy Framework Directive by 2020 • Reduction of anthropogenic nutrient flows to the Adriatic and Ionian seas to ensure that by 2021 eutrophication is minimised Reduction of marine litter in line with Marine Strategy Framework Directive and 7th Environment Action Programme targets by 2020 • A joint contingency plan for oil spills and other large scale pollution events adopted by 2016 and measures to enable joint and coordinated emergency response implemented by 2020 • Establishment of transnational management plans for all terrestrial eco-regions, shared by two or more participating countries • Adoption of maritime spatial planning and integrated coastal management strategies by EU Member State by 2017 and for coastal candidate and potential candidate Countries by 2018 | Implementarion report of EUSAIR Action Plan in 2020+ and Annual reports of TSG3 | No quorum at the meeting. The EUSAIR Implementation plan will not be implemented
Expected results | Addressing the threats to biodiversity caused by human activities, like deterioration of water quality (in particular impact of marine litter, micro plastic and chemical pollutants) and because of climate change. | What are the indicators to measure whether and to what extent the action achieves the expected results? - Common solution to be foreseen in the project implementation phase about: legal bases, governance and technical aspects. - Identification of stakeholders - Pilot project - Pilot monitoring activities | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
Activities | What are the key activities to be carried out and in what sequence in order to produce the expected results? (group the activities by result) WP:preparation activities - TSG 3 EUSAIR preparation conferences and meetings Other WP: - Drafting a proposal for concrete measures for monitoring and management of marine protected species. - Developing an Adriatic-Ionian Observatory to improve data collecting and sharing. - Identification of hot spot marine biogenic formations that are excluded from Marine protected areas or are not adequately managed within those with pilot monitoring to assess their environmental status and preparation of common sampling protocols. - Evaluating the status of the selected marine protected species due to risks related to pollutants (e.g. marine litter, microplastics) and climate change with the support of pilot projects. - Preparing a plan for raising awareness education of stakeholders, local communities and tourist on the effects of tourism, human activities as such and of marine litter on marine protected species and popularisation through citizen science. -The excellent back ground for the project are the results and outputs of the Trecorala, ClimaParks, ActionMed, MEDCIS, NetCet, Tartalife, DeFishGear and other relevant projects (studies, analysis and protocols). | Means: What are the means required to implment these activities; personel, equipment, trining, studies, supplies, operational facilities etc. PARTNERS Potential project partners: MONTENEGRO: Environment and Nature Protection Agency (milena.batakovic@epa.org.me), Institute for Marine Biology (mamilica@ac.me) | What are the sources of infomration about action progress. COSTS What are the action costs? Hoe are they classified? (Budget for Action Brakdown) | What pre-conditions are required before the action starts? What condistions outside the Beneficary's direct control have to be met for the implementation of planned activities?

## LF Serbia
LOGICAL FRAMEWORK 3MPS
| Intervention logic | Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall Objective | This overall objective of the pillar is to address the issue of environmental quality, with respect to marine, coastal and terrestrial ecosystems in the Region. Environmental quality is essential for underpinning human activities in the Region and for ensuring economic and social well-being for its peoples. The pillar will deal with the environmental issues that can only be adequately tackled through cooperation at the level and scale of the macro-region. | At least 3 actions, project activities in line with the specific objectives. Additional one TSG3 meeting per year and workshops | Annual Reports of TSG 3 and GB EUSAIR
Specific Objective | 1. To ensure a good environmental and ecological status of the marine and coastal environment by 2020 in line with the relevant EU acquis and the ecosystem approach of the Barcelona Convention. 2. To contribute to the goal of the EU Biodiversity Strategy to halt the loss of biodiversity and the degradation of ecosystem services in the EU by 2020, and restore them in so far as feasible, by addressing threats to marine and terrestrial biodiversity. 3. To improve waste management by reducing waste flows to the sea and, to reduce nutrient flows and other pollutants to the rivers and the sea. | • Establishment of a common infrastructure platform with participation of all countries for data collection, research, and laboratory analysis by end of 2015 • 10% surface coverage of Adriatic and Ionian Seas by Marine Protected areas26 • Enhancement of NATURA 2000 and Emerald networks in the Region • Achieving Good Ecological Status of the Adriatic and Ionian Seas by 2020 • Enhancement of a marine NATURA 2000 network and a coherent and representative network of MPAs under the Marine Strategy Framework Directive by 2020 • Reduction of anthropogenic nutrient flows to the Adriatic and Ionian seas to ensure that by 2021 eutrophication is minimised Reduction of marine litter in line with Marine Strategy Framework Directive and 7th Environment Action Programme targets by 2020 • A joint contingency plan for oil spills and other large scale pollution events adopted by 2016 and measures to enable joint and coordinated emergency response implemented by 2020 • Establishment of transnational management plans for all terrestrial eco-regions, shared by two or more participating countries • Adoption of maritime spatial planning and integrated coastal management strategies by EU Member State by 2017 and for coastal candidate and potential candidate Countries by 2018 | Implementarion report of EUSAIR Action Plan in 2020+ and Annual reports of TSG3 | No quorum at the meeting. The EUSAIR Implementation plan will not be implemented
Expected results | Addressing the threats to biodiversity caused by human activities, like deterioration of water quality (in particular impact of marine litter, micro plastic and chemical pollutants) and because of climate change. | What are the indicators to measure whether and to what extent the action achieves the expected results? - Common solution to be foreseen in the project implementation phase about: legal bases, governance and technical aspects. - Identification of stakeholders - Pilot project - Pilot monitoring activities | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
Activities | What are the key activities to be carried out and in what sequence in order to produce the expected results? (group the activities by result) WP:preparation activities - TSG 3 EUSAIR preparation conferences and meetings Other WP: - Drafting a proposal for concrete measures for monitoring and management of marine protected species. - Developing an Adriatic-Ionian Observatory to improve data collecting and sharing. - Identification of hot spot marine biogenic formations that are excluded from Marine protected areas or are not adequately managed within those with pilot monitoring to assess their environmental status and preparation of common sampling protocols. - Evaluating the status of the selected marine protected species due to risks related to pollutants (e.g. marine litter, microplastics) and climate change with the support of pilot projects. - Preparing a plan for raising awareness education of stakeholders, local communities and tourist on the effects of tourism, human activities as such and of marine litter on marine protected species and popularisation through citizen science. -The excellent back ground for the project are the results and outputs of the Trecorala, ClimaParks, ActionMed, MEDCIS, NetCet, Tartalife, DeFishGear and other relevant projects (studies, analysis and protocols). | Means: What are the means required to implment these activities; personel, equipment, trining, studies, supplies, operational facilities etc. PARTNERS | What are the sources of infomration about action progress. COSTS What are the action costs? Hoe are they classified? (Budget for Action Brakdown) | What pre-conditions are required before the action starts? What condistions outside the Beneficary's direct control have to be met for the implementation of planned activities?

## LF Slovenia
LOGICAL FRAMEWORK 3MPS
| Intervention logic | Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall Objective | This overall objective of the pillar is to address the issue of environmental quality, with respect to marine, coastal and terrestrial ecosystems in the Region. Environmental quality is essential for underpinning human activities in the Region and for ensuring economic and social well-being for its peoples. The pillar will deal with the environmental issues that can only be adequately tackled through cooperation at the level and scale of the macro-region. | At least 3 actions, project activities in line with the specific objectives. Additional one TSG3 meeting per year and workshops | Annual Reports of TSG 3 and GB EUSAIR
Specific Objective | 1. To ensure a good environmental and ecological status of the marine and coastal environment by 2020 in line with the relevant EU acquis and the ecosystem approach of the Barcelona Convention. 2. To contribute to the goal of the EU Biodiversity Strategy to halt the loss of biodiversity and the degradation of ecosystem services in the EU by 2020, and restore them in so far as feasible, by addressing threats to marine and terrestrial biodiversity. 3. To improve waste management by reducing waste flows to the sea and, to reduce nutrient flows and other pollutants to the rivers and the sea. | • Establishment of a common infrastructure platform with participation of all countries for data collection, research, and laboratory analysis by end of 2015 • 10% surface coverage of Adriatic and Ionian Seas by Marine Protected areas26 • Enhancement of NATURA 2000 and Emerald networks in the Region • Achieving Good Ecological Status of the Adriatic and Ionian Seas by 2020 • Enhancement of a marine NATURA 2000 network and a coherent and representative network of MPAs under the Marine Strategy Framework Directive by 2020 • Reduction of anthropogenic nutrient flows to the Adriatic and Ionian seas to ensure that by 2021 eutrophication is minimised Reduction of marine litter in line with Marine Strategy Framework Directive and 7th Environment Action Programme targets by 2020 • A joint contingency plan for oil spills and other large scale pollution events adopted by 2016 and measures to enable joint and coordinated emergency response implemented by 2020 • Establishment of transnational management plans for all terrestrial eco-regions, shared by two or more participating countries • Adoption of maritime spatial planning and integrated coastal management strategies by EU Member State by 2017 and for coastal candidate and potential candidate Countries by 2018 | Implementarion report of EUSAIR Action Plan in 2020+ and Annual reports of TSG3 | No quorum at the meeting. The EUSAIR Implementation plan will not be implemented
Expected results | Addressing the threats to biodiversity caused by human activities, like deterioration of water quality (in particular impact of marine litter, micro plastic and chemical pollutants) and because of climate change. | What are the indicators to measure whether and to what extent the action achieves the expected results? - Common solution to be foreseen in the project implementation phase about: legal bases, governance and technical aspects. - Identification of stakeholders - Pilot project - Pilot monitoring activities | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
Activities | What are the key activities to be carried out and in what sequence in order to produce the expected results? (group the activities by result) WP:preparation activities - TSG 3 EUSAIR preparation conferences and meetings Other WP: - Drafting a proposal for concrete measures for monitoring and management of marine protected species. - Developing an Adriatic-Ionian Observatory to improve data collecting and sharing. - Identification of hot spot marine biogenic formations that are excluded from Marine protected areas or are not adequately managed within those with pilot monitoring to assess their environmental status and preparation of common sampling protocols. - Evaluating the status of the selected marine protected species due to risks related to pollutants (e.g. marine litter, microplastics) and climate change with the support of pilot projects. - Preparing a plan for raising awareness education of stakeholders, local communities and tourist on the effects of tourism, human activities as such and of marine litter on marine protected species and popularisation through citizen science. -The excellent back ground for the project are the results and outputs of the Trecorala, ClimaParks, ActionMed, MEDCIS, NetCet, Tartalife, DeFishGear and other relevant projects (studies, analysis and protocols). | Means: What are the means required to implment these activities; personel, equipment, trining, studies, supplies, operational facilities etc. PARTNERS Potential project partners: SLOVENIA: National Institute of Biology (NIB), Marine Biology Station, Večna pot 111, 1000 Ljubljana, David Stanković <David.Stankovic@nib.si>, patricija.mozetic@nib.si, branko.cermelj@nib.si Institute for Water of the Republic of Slovenia, Dunajska cesta 156, 1000 Ljubljana | What are the sources of infomration about action progress. COSTS What are the action costs? Hoe are they classified? (Budget for Action Brakdown) | What pre-conditions are required before the action starts? What condistions outside the Beneficary's direct control have to be met for the implementation of planned activities?