## Slide 1
EUSAIR Youth Council
Point 3 - List of EYC candidates and GB approval process
9th Task Force meeting
Online, 11 September 2024

## Slide 2
1994 4
1995 19
1996 16
1997 16
1998 18
1999 24
2000 14
2001 13
2002 15
2003 13
2004 13
2005 12
2006 1
From list of selected candidates to final EYC members
As agreed at the last TF (27.5.2024):
  Report from the assessment/selection process and presentation of list of candidates at Autumn TF
  Approval of list of candidates and reserve list by GB after TF with shortened procedure of 1 week
  TF members to communicate with NCs to clarify any questions/concerns

## Slide 3
Task Time
End of Consolidation period AUGUST 15 - SEPTEMBER 9
List of 20 selected members and 20 reserve members SEPTEMBER 10
9th TASK FORCE meeting SEPTEMBER 11
Written Procedure for approval of the list by the Governing Board 12-19 SEPTEMBER
Notification letters sent to selected candidates (with letter of commitment to be signed) 23 SEPTEMBER
Final list of committed members. 7 OCTOBER
Online meeting with EYC members regarding next steps and organisation of the inauguration meeting & contacting those who were not selected MID OCTOBER
Inauguration meeting of EUSAIR Youth Council Members with capacity building in Croatia END OF NOVEMBER/TBD
PUBLIC INNAUGURATION EVENT in Greece FEB/MARCH 2025/TBD
Possible Next Steps Towards EYC 2024 Set-up
Task | Time
List of 20 selected candidates and 20 reserve candidates | SEPTEMBER 10
9th TASK FORCE meeting | SEPTEMBER 11
GB Written Procedure for approval of the lists | 17-26 SEPTEMBER
Notification letters sent to selected candidates (with letter of commitment to be signed) | 27 SEPTEMBER
Any possible replacement from the reserve list | 27 SEPTEMBER – 11 OCTOBER
Final list of committed members | 11 OCTOBER

## Slide 4
Task Time
End of Consolidation period AUGUST 15 - SEPTEMBER 9
List of 20 selected members and 20 reserve members SEPTEMBER 10
9th TASK FORCE meeting SEPTEMBER 11
Written Procedure for approval of the list by the Governing Board 12-19 SEPTEMBER
Notification letters sent to selected candidates (with letter of commitment to be signed) 23 SEPTEMBER
Final list of committed members. 7 OCTOBER
Online meeting with EYC members regarding next steps and organisation of the inauguration meeting & contacting those who were not selected MID OCTOBER
Inauguration meeting of EUSAIR Youth Council Members with capacity building in Croatia END OF NOVEMBER/TBD
PUBLIC INNAUGURATION EVENT in Greece FEB/MARCH 2025/TBD
Possible Next Steps After EYC 2024 Set-up
Task | Time
Final list of committed members | 14 OCTOBER
Online meeting with EYC members regarding next steps and organisation of the inauguration meeting & contacting those who were not selected | MID OCTOBER
1st Membership and Capacity Building Meeting of EYC in Croatia (division of tasks and timeline) | END OF NOVEMBER/TBD
EUSAIR Youth Council Inaugural Networking Event in Greece and possibly the 2nd EYC meeting (1st RoP draft, EYC at 10th Forum) | FEB/MARCH 2025/TBD

## Slide 5
Task Time
End of Consolidation period AUGUST 15 - SEPTEMBER 9
List of 20 selected members and 20 reserve members SEPTEMBER 10
9th TASK FORCE meeting SEPTEMBER 11
Written Procedure for approval of the list by the Governing Board 12-19 SEPTEMBER
Notification letters sent to selected candidates (with letter of commitment to be signed) 23 SEPTEMBER
Final list of committed members. 7 OCTOBER
Online meeting with EYC members regarding next steps and organisation of the inauguration meeting & contacting those who were not selected MID OCTOBER
Inauguration meeting of EUSAIR Youth Council Members with capacity building in Croatia END OF NOVEMBER/TBD
PUBLIC INNAUGURATION EVENT in Greece FEB/MARCH 2025/TBD
EYC 2025 Call for Applications
Task | Time
Members appointed in 2024 to notify the TF about their commitment to continue for another year | END OF MARCH
Call in countries with missing members | APRIL
Assessment/Selection | MAY-JUNE
Final list of members for EYC 2025 | SEPTEMBER
Reserve list 2024 active until March 2026 | 

## Slide 6
Task Time
End of Consolidation period AUGUST 15 - SEPTEMBER 9
List of 20 selected members and 20 reserve members SEPTEMBER 10
9th TASK FORCE meeting SEPTEMBER 11
Written Procedure for approval of the list by the Governing Board 12-19 SEPTEMBER
Notification letters sent to selected candidates (with letter of commitment to be signed) 23 SEPTEMBER
Final list of committed members. 7 OCTOBER
Online meeting with EYC members regarding next steps and organisation of the inauguration meeting & contacting those who were not selected MID OCTOBER
Inauguration meeting of EUSAIR Youth Council Members with capacity building in Croatia END OF NOVEMBER/TBD
PUBLIC INNAUGURATION EVENT in Greece FEB/MARCH 2025/TBD
Youth4Cooperation - Post 2027 Youth Consultation
  Event organised by DG REGIO
  15 November, Brussels – Youth in post 27 Interreg (event to involve youth in shaping post 27 Cohesion Policy)
  100 young people including delegation from MRS YCs
  Deadline for communicating EYC delegation members – latest 11 September
  Proposal: 3 candidates with highest assessment score to be asked to participate as representatives of EYC . If/when the candidate list is approved they become delegates

## Slide 7: Thank you for a constructive meeting!