## Slide 1
EUSAIR Governance Support Project 2
StEP
Stakeholder Engagement and Embedding
Meeting between EUSAIR Pillar Coordinators and
EUSAIR Governance Point
online, 12 September 2024

## Slide 2
LAUNCHING AND CLOSURE OF 2 MICRO-TENDERS FOR A TEMPORARY ASSIGNMENT OF EXPERTS FOR
1)COMMUNITY AND CONTENT MANAGEMENT AND FOR 2)FINANCIAL DIALOGUE/ EMBEDDING
Market research launched on May 2° (Economic Development Department Decree n°170)
Published on EUSAIR Website and ESP Platform for the assessment of the transboundary interest
Awarded to t33 SRL Company
Kick-off meeting held in Ancona on September 2°
Signature of the 12 months contract to be expected soon

## Slide 3
WP1 and WP2
COMMUNITY and CONTENT MANAGEMENT
Workplan
Sept 2024-Aug 2025
Support the StEP Digital Management Team
Asynchronous learning modules (MOOCs)
Technical assistance to ESP Stakeholders
Digital mapping of funding opportunities 2021-2027
Management of the repository
Preparation of web communication tools
Support in the organization of events
t33

## Slide 4
SUPPORTING THE EUSAIR FINANCIAL DIALOGUE AND THE EMBEDDING INTO COHESION POLICY
Workplan
Sept 2024-Aug 2025
Financial dialogue BACKGROUND and METHODOLOGICAL PAPER
MAs network BACKGROUND AND METHODOLOGICAL APPROACH PAPER
Collection of materials for DESK REVIEW REPORT
Reactivation of
EUSAIR ACTION LABS for ETC MAs
ON-LINE TRANSNATIONAL EVENTS FOR MAINSTREAM MAs
t33
t33
WP4

## Slide 5
SUPPORTING THE EUSAIR EMBEDDING INTO IPAIII PROGRAMMES
29° July 2024: signature of the contract
Tendering procedure under PRAG regulations launched and finalized
WP5
Awarded to Naxta SRL Company
WP leader: DEI

## Slide 6
Next steps
  B2B meetings with Pillar Coordinators for the preparatory development of ESP Database (Fall 2024)
Having the procedure above the EU threshold officially launched by December 2024
Reactivation of the ETC MAs network (3 Action labs webinar events from December 2024 to July 2025)
On-line transnational events for Mainstream MAs (Spring/Summer 2025)

## Slide 7
Public procurement tender for a technical assistance company above the EU threshold
From Sept 2025
to Dec 2027
Preliminary market consultation according to art. 77 D.Lgs. 36/2023 launched on July 22° (Economic Development Department decree n° 344)
Published on EUSAIR Website and ESP Platform for the assesment of the transboundary interest
Deadline for submitting contributions postponed from August 30° to September 20°,
procedure still ongoing
Preliminary contributions received from ICT companies and start-ups

## Slide 8
Public procurement tender for a technical assistance company above the EU threshold: WP1 and WP2
User management and profiling
What
is StEP
expecting for ESP upgrade?
Real-time cooperation environment for different stakeholder groups
Multilingual automatic transcription and translation
AI-based applications
Enhanced e-learning functionalities
Data knowledge management
Integration with models and applications already developed
Setting up and animating the EUSAIR financial dialogue
From Sept 2025
to Dec 2027

## Slide 9
Public procurement tender for a technical assistance company above the EU threshold: WP4
What
is StEP
expecting for financial dialogue and embedding
From Sept 2025
to Dec 2027
Financial dialogue
on-line MATCHMAKING ENVIRONMENT
PERMANENT ACTION LABs : permanent laboratory for ETC MAs network
Establishment of the MAINSTREAM MAs NETWORK
GUIDANCE PAPERS for:
development of MAs networks
- for embedding in 2028-2032 progr. period

## Slide 10
THANK YOU FOR YOUR ATTENTION
StEP working group